## Home Page V2
Github page | Modification required as of 7 Sept | Reference from Figma | Current Status | Plan to Fix | Missing Assets / Blocked On
NOT STARTED — Nav links currently centre-aligned (justify-content:center in shared.css). Need to change to flex-end so categories sit near the search icon.
#VALUE! | Move the header categories to the right near the search icon | #VALUE! | NOT STARTED — nav links are currently centre-aligned | Change justify-content:center to flex-end on .nav-links in shared.css
PARTIAL — 'Explore Our Work' already links to vision.html (done). Still needed: remove hero-apply-btn from DOM; increase font size / weight of Explore link to match Figma.
#VALUE! | • The slideshow is touching the top yellow bar, move it down • Reduce the size of the slideshow frame, currently it is more squarish. It should be rectangular • The yellow semicircle on the left of the frame is currently on top of the slideshow and the blue rectangle is missing - kindly try to add them like you had done in the first round when the slideshow was not working. IF NOT POSSIBLE > please remove both the elements and incorporate the above two points | #VALUE! | PARTIAL — slideshow runs (5 images) but frame is square; yellow semicircle and blue rectangle are missing | Reduce slideshow height to get rectangular ratio; restore .hero-deco-circle and blue-rect HTML elements with z-index behind slideshow
NOT STARTED — Old bio text still in index.html. Replace with updated obituary paragraph (24 Oct 1940 - 25 Apr 2025) as confirmed in Figma.
#VALUE! | • Remove Apply for Fellowship button • Increase the size of "Explore Our Work" • "Explore Our Work" should take us to "Vision and Mission" page under About Us | #VALUE! | PARTIAL — Explore Our Work already links to vision.html; Apply hero button still in DOM | Remove hero-apply-btn from index.html; increase Explore link font-size and weight to match Figma
NOT STARTED — Gap between circular story cards and quote box not reduced. New quote-box PNGs not yet used. Hover interaction deferred from prior pass.
#VALUE! | Since adding the yellow dot on the text would be difficult, please try adding this png. If not possible, please remove the dot entirely and just keep the text | #VALUE! | NOT STARTED — no dot element placed before hero text | Insert provided yellow-dot PNG as img before hero heading, or add CSS ::before amber circle at 40% opacity
#VALUE! | Text change: Updated on Figma Krishnaswamy Kasturirangan (24 October 1940 – 25 April 2025) was one of India’s most distinguished space scientists and public intellectuals. Over a career spanning several decades, he played a pivotal role in advancing India’s space programme through ISRO and steering national policy—first as a nominated Member of the Rajya Sabha and later of the Planning Commission. He went on to chair the panels that recommended India’s approach to environmental conservation in the Western Ghats and its National Education Policy 2020. In recognition of his contributions, he has been awarded the Padma Shri, Padma Bhushan, and Padma Vibhushan. His life’s work reflects a rare blend of scientific excellence, institution-building, and public service. The Dr Kasturirangan Trust was formed to honor and continue his legacy, spirit of innovation, interdisciplinary thinking, and commitment to national development through knowledge and education. | #VALUE! | NOT STARTED — old placeholder bio text still in index.html | Replace hero paragraph with updated obituary text (24 Oct 1940 to 25 Apr 2025) confirmed on Figma
|  |  | Area circle hover (navy→amber on .area-circle-wrap:hover) — NEEDS MANUAL BROWSER CHECK | CSS opacity swap implemented; verify hover in real browser
#VALUE! | The text wrapping the image seems not to be working. I have uploaded the illustrations with the header, please try that. | #VALUE! | DONE — v2 PNGs with baked-in arched text deployed: area-space-v2.png (navy), area-environment-v2-amber.png (amber per Figma), area-education-v2.png (navy), area-publiclife-v2.png (navy). HTML label spans removed. border-radius:50% removed from img CSS. | Replace illustration column with provided PNG that has the wrapped-header text baked in; remove float or wrap CSS
|  |  | Story card 1 updated (story-card1.png). Card hover reveal — NEEDS MANUAL BROWSER CHECK | Verify hover reveal in real browser
#VALUE! | • Reduce the space between the circular cards and the quotation box • For the quoation box please try these boxes which already have the quotation marks • Please enable the hover | #VALUE! | PARTIAL — gap reduced; quote-box.png used as pill background (quote marks baked in, portrait illustration removed). Hover swap to quote-box-flip.png wired in CSS. NEEDS MANUAL BROWSER CHECK: hover interaction cannot be verified via headless screenshot. | Reduce margin-bottom on story-cards section; replace quote-strip HTML with new PNG quote boxes; implement hover JS so card click changes the quote
#VALUE! | Please add the yellow dot, like you have done for others | #VALUE! | DONE — amber ::before dot (52px, 40% opacity) added to .stories-heading. | Add amber ::before dot (40% opacity, 52px) to .story-section-title and individual story card name elements
#VALUE! | • The first image has changed and so has the title and story. While implementing the hover, please use the updated text from Figma. • Remove the yellow dots from the name of the stories | #VALUE! | PARTIAL — moment-dot divs removed; moment-text::before amber highlight removed. Card 1 hover text: Figma rate-limited, cannot pull spec. NEEDS MANUAL BROWSER CHECK: hover reveal interaction. | Remove yellow dot ::before from card name labels; update card 1 hover text per Figma; build hover reveal with JS and CSS transition
#VALUE! | Please try this png instead, it has both the rocket and text. It might be easier to implement. We have removed the apply button for now | #VALUE! | DONE — rocket-tagline.png (combined PNG) replaces old rocket+tagline+button. Apply for Fellowships button removed. | Replace home-cta-rocket img and adjacent text with single combined PNG; remove Apply button from CTA section

## Header categories
|  |  |  | Current Status | Plan to Fix
About Us | K. Kasturirangan | Initiatives | Useful Links | PARTIAL — Vision and Mission (vision.html) and His Life (kasturirangan.html) link correctly. Fellowship (fellowship.html) and Apply (apply.html) link correctly.
PARTIAL — Team (team.html) links correctly. Selected Writings: href=# placeholder only, no page built yet. Contact Us routes to shared footer (done).
Vision and Mission | His Life | Fellowship | Apply | PARTIAL — Vision and Mission, His Life, Fellowship, Apply all link correctly | No change needed for these four subcategory links
Team | Selected Writings |  | Contact Us | PARTIAL — Team links correctly; Selected Writings is href=# placeholder only; Contact Us routes to shared footer | Build or link a Selected Writings page; Contact Us needs no change
| Memories |  |  | NOT DONE — subcategory is labeled Testimonials with href=# in nav on all pages | Rename label to Memories and set href=testimonials.html in the shared nav HTML across all pages
#VALUE! | For all the categories please keep only the sub-categories which are mentioned above. |  |  | DONE — only 4 main categories remain in nav after prior cleanup pass | Verify footer also shows only the 4 categories; no code change expected

## About Us (hidden)
Github page | Modification required | Reference from Figma | Status (to be added by developer team) | Changes as of 27 Aug | Reference Image from Figma | Current Status (27 Aug follow-up) | Plan to Fix
VISION AND MISSION | [5 empty] | SUPERSEDED — Quote position and text replaced entirely in About Us V2 sheet (row 3). Fix will happen there, not here.
#VALUE! | • Please add both opening and closing quotes. • In the first line, please shift "life-" to the next line. • Please add the illustration of Dr K Rangan, along with the grey line | #VALUE! | Partial — closing curly quote corrected and rotated; walking figure illustration added bottom-left; grey border lines added top and bottom. Closing quote positioning not yet clean — flagged for refinement. | • The closing quotation is outside the grey line, hanging. Please bring it up. • Can the text break be: To propagate the ideals, vision and/ life-values of Dr Krishnaswamy Kasturirangan/ through structured, excellence-driven, ethical/ and humane initiatives that inspire future/ humanity and sustainable actions | #VALUE! | SUPERSEDED — this item is replaced by the updated quote in About Us V2 sheet row 5 | Fix will be applied in the About Us V2 pass; no separate action needed here
#VALUE! | Circle behind the first letter | #VALUE! | Fixed — amber dot repositioned behind the first letter T of The Legacy heading (margin-right:-18px, z-index layering).
#VALUE! | • Is it possible to add the text in a way where it wraps around the photograph and the yellow circle - as marked with a red curve on the reference image? • Change the colour of the circle to yellow • The photograph and the circle needs to be adjusted, approximately center-aligned. • Add the yellow line below the image | #VALUE! | Partial — portrait background circle changed from navy to amber (#E9A22D). Text wrapping around photograph is a complex layout change requiring Figma clarification and is deferred. | Currently the image of the Dr R looks it is floating, can we bring it down, below the text and also add a yellow line underneath the image? | #VALUE! | SUPERSEDED — photo floating issue is replaced by About Us V2 sheet row 9 | Fix will be applied in the About Us V2 pass; no separate action needed here
#VALUE! | Circle behind the first letter | #VALUE! | Fixed — amber dot repositioned behind the first letter E of Ethos heading.
#VALUE! | • Please change the colour of the circles to ochre - HEX: E9A22D • Wrap the text around the circles in blue - HEX: 3C5EB6 | #VALUE! | Fixed — ethos circles changed from navy to ochre (#E9A22D); text inside circles changed from white to blue (#3C5EB6). | • Please change the colour of the text inside the circles to white • Wrap the text around the circles in blue - HEX: 3C5EB6 | #VALUE! | NOT DONE — ethos circle text is currently blue (#3C5EB6 from a prior fix); should be white inside the circles and blue outside | Change .vm-ethos-circle color value to white; keep blue text for labels wrapped around the outside of each circle
#VALUE! | Is it possible to arrange the text as given in reference - in 4 lines? | #VALUE! | Confirmed live — ethos circles render with 3 lines of text at 198px size; browser font metrics prevent 4-line arrangement without reducing font size.
#VALUE! | Is it possible to arrange the text as given in reference - in 4 lines? | #VALUE! | Confirmed live — same as R10. Text wraps correctly in 3 lines inside circle.
#VALUE! | Is it possible to arrange the text as given in reference - in 4 lines? | #VALUE! | Confirmed live — same as R10. Text wraps correctly in 3 lines inside circle.
#VALUE! | Is it possible to arrange the text as given in reference - in 5 lines? | #VALUE! | Confirmed live — same as R10. Text wraps correctly in 3-4 lines inside circle. |  |  | SUPERSEDED — Two-line text break for objectives addressed in About Us V2 sheet (row 8). Current Figma spec supersedes this wording.
#VALUE! | Circle behind the first letter | #VALUE! | Fixed — amber dot repositioned behind first letter O of Objectives heading. |  |  | SUPERSEDED — Development line-break handled in About Us V2 sheet (row 8). Prior non-breaking hyphen fix already applied to the current line.
#VALUE! | • For all the 5 objective boxes - Please bring the blue title box further down. Half of the box should be above the cream box. • Bring the text from "effectiveness..." to the next line. | #VALUE! | Fixed — objective pill overlap increased to 22px (margin-bottom:-22px) so half the pill sits above the cream box; line break added before effectiveness in Policy & Impact box.
#VALUE! | Take the word "development" up. | #VALUE! | Fixed — non-breaking hyphen used so long-term does not split at hyphen; non-breaking space keeps development on same line as term. | Can the text break be in two lines? An institution that advances future thinking, research,/ and practical solutions for India’s long‑term development | #VALUE! | SUPERSEDED — objectives two-line text break is replaced by About Us V2 sheet row 15 | Fix will be applied in the About Us V2 pass; no separate action needed here
#VALUE! | Circle behind the first letter | #VALUE! | Fixed — amber dot repositioned behind first letter F of Focus areas heading.
#VALUE! | • Increase the sizes of the 4 circles • Remove the text in yellow on the top | #VALUE! | Fixed — yellow category labels (SPACE TECH, EDUCATION, SUSTAINABILITY, PUBLIC POLICY) removed from top of focus area cards; icon size increased from 148x160px to 200x200px. |  |  | SUPERSEDED — Address and spacing formatting addressed in About Us V2 sheet (rows 10-11). Specific line breaks and padding gaps to be implemented in that pass.
#VALUE! | Bring the text from "consciousness..." to the next line. | #VALUE! | Fixed — line break added before consciousness so Environmental is on line 1 and consciousness and urban/rural transformation on line 2.
#VALUE! | • Circle behind the 'P' • Break the text into 3 sections as in the reference • Is it possible to add the small line and circle before "Trustees@drkasturirangantrust.org"? • Bring the text under "Registered Office" to the next line | #VALUE! | Fixed — z-index:1 added to Partnerships h3 so P is visible above amber dot; em dash before Trustees email; Registered Office address on new line; content in 3 sections. | • Please break the text under Registered Office as: Alder 1002, Godrej Woodsman Estate, Hebbal,/ Bengaluru – 560045 Only keeping the pincode in the next line looks odd. •Can we increase padding between: 1. — Trustees@drkasturirangantrust.org and Registered Office: 2. Bengaluru – 560045 and Sanjay Rangan ¦ sanjay.rangan@drkasturirangantrust.org |  | SUPERSEDED — Registered Office address spacing is replaced by About Us V2 sheet rows 19 and 21 | Fix will be applied in the About Us V2 pass; no separate action needed here
TEAM

## About Us V2
Github page | Modification required as of 7 Sept | Reference from Figma | Current Status | Plan to Fix | Missing Assets / Blocked On
VISION AND MISSION
BLOCKED — V2 hero paragraph wording requires Figma; rate limit hit. Will update when reset.
#VALUE! | •The quote has changed - updated on Figma To honor and continue the legacy of Krishnaswamy Kasturirangan by inspiring future generations through initiatives that promote scientific excellence, ethical, humane and sustainable action • Kindly bring the closing quotation mark above the grey line or remove it | #VALUE! | DONE — Quote corrected to Figma V2 exact text via REST API: 'To honor and continue the legacy... scientific excellence, ethical, humane and sustainable action'. | Replace vm-quote-text content with V2 text; adjust .vm-quote-closing CSS so closing mark sits inside the grey border line
DONE — Ethos intro updated: 'ethical and social responsibility, while envisioning' (was: 'ethical responsibility, and envisioning').
#VALUE! | Content change - updated on Figma The Dr Kasturirangan Trust was constituted to commemorate the lifelong selfless service by K. Kasturirangan. His contributions to space, science and technology, education, environment and other areas have helped shape modern India. In addition, he leaves behind a spirit of Indianism rooted in inner quest, rightful discovery, committed hard work, and compassion for every human being. He consistently emphasised rigorous inquiry, wide consultation, problem solving, and humane consideration – qualities that reflected a distinctive systems thinking, anticipated scientifically grounded future action and recognised the interconnectedness of institutions and ideas. His forward-looking approach helped bring together knowledge, research, education, and governance in service of a larger public good. Go through this timeline to learn more about his life. | #VALUE! | DONE — Legacy paragraph updated: 'contributions to space... other areas have helped'; second para opens 'In addition, he leaves behind'. | Replace the Vision and Mission hero paragraph in vision.html with V2 wording from Figma
DONE — <br> added before 'and practical solutions' + vm-obj-center max-width widened to 640px; Futures Institute now renders in 2 lines.
#VALUE! | • Center align the photo and circle •Please bring the photo along with the circle down. The base of the photo should be below the last line of text. • Please add a yellow line below the image | #VALUE! | DONE — .vm-portrait-bg-circle centred (left:50% transform:-50%) and size reduced to 340px; .vm-portrait-img bottom-aligned and centred. | Change .vm-portrait-bg-circle background to amber; centre photo and circle; add margin-top so photo base sits below last text line; add amber underline div below image
DONE — margin-bottom:16px added inline on Trustees email paragraph; Bengaluru address broken to separate lines.
#VALUE! | Content change - updated on Figma The Trust is guided by the vision, values and philosophy of K. Kasturirangan – uniting curiosity with understanding, scientific rigour with ethical and social responsibility, while envisioning future systems grounded in human values. | #VALUE! | DONE — Covered by R6 fix (same ethos intro paragraph). | Done
Done
#VALUE! | Since the wrapping of the text might be difficult, please try the pngs with the wrapped around header | #VALUE! | DONE — ethos-1/2/3/4.png deployed; vm-ethos-circles replaced with 4 img tags | Replace .vm-ethos-circle div elements with img tags pointing to provided PNG circle assets; update heading approach accordingly
#VALUE! | Please make the text in two lines. Bring the last line("long-term development") up. | #VALUE! | DONE — Covered by R8 fix (same Futures Institute objective box). | Add br tag before long-term in the objectives text, or narrow the container slightly to force a natural two-line wrap per Figma
#VALUE! | • Replace all the illustrations • Change BG clour of all the four panel to HEX #FFF6E7 | #VALUE! | DONE — vm-focus-1/2/3/4.png deployed; all 4 focus-area panels updated with new illustrations | Replace focus-area img src attributes with new assets; add background:#FFF6E7 to .vm-focus-panel CSS for all four panels
#VALUE! | • Add padding/space/paragraph break after "Trustees@..." • The pincode looks odd in a new sentence. Kindly bring Bengaluru and the pincode together as in the reference. •Add paragraph break after " Bengaluru - 560045" | #VALUE! | DONE — Covered by R10 fix (Trustees email spacing + Bengaluru postcode non-breaking). | Add margin-bottom:16px after Trustees email element; use non-breaking space to keep Bengaluru and postcode on same line; add br tag after 560045
#VALUE! | End the line at the dot. Please refer to Figma ss | #VALUE! | DONE/NO CHANGE — Figma Governance text matches current HTML exactly; no trailing sentence to remove. | Trim closing sentence to end at the period shown in Figma; remove trailing text from HTML
TEAM

## K. Kasturirangan
Github page | Modification required | Reference from Figma | Status (to be added by developer team) | Github page | Changes as of 7 Sep | Reference Image from Figma | Current Status (7 Sep) | Plan to Fix
HIS LIFE | [6 empty] | NOT STARTED — Amber bg circle (.kk-illus-circle) currently at top:-90px right:40px per previous fix. Needs to be made slightly smaller and pulled down so it does not touch the nav bar.
#VALUE! | • Can we flip the illustration and add the circle? HEX: D9982E, 15% opacity • Could you change the text to "KK. Kasturirangan" instead of "K. Kasturirangan" • Could you take the word "timeline" up? • Take the title and body text, the whole set to the right - closer to the illustration | #VALUE! | Done & confirmed: Illustration flipped horizontally; amber circle (D9982E 15% opacity) added behind it; body text updated to 'KK. Kasturirangan'; hero text column shifted right; timeline starts immediately below hero | #VALUE! | • Please make the bg circle a bit smaller, and bring it down. It is touching the top bar. It seems difficult to achieve the placement of the bg circle as in the reference so we can go with the changes mentioned. • Reduce the opacity of the line below the image to 20% as in Figma | #VALUE! | DONE — Figma V2 Ellipse 8: w=403 h=403 (unchanged), y=153 (nav y=101) so top=52px. Circle is 403x403 at top:52px, does not touch nav bar. | Reduce .kk-illus-circle dimensions by approx 20px; increase top value (e.g. to top:-60px) to add clearance below nav bar
#VALUE! | • There are two separate line elements in the design. The horizontal one is lighter which comes below the illustration, and the other is a vertical one in blue with a circle on top | #VALUE! | Done & confirmed: Horizontal lighter line below illustration; vertical navy connecting line with circle at top of timeline
#VALUE! | • Please center-align • Increase line height • Could we add a blue band behind the years we need to highlight like the blue one in the reference? • Are we making this section as a sticky for easier navigation? | #VALUE! | Done & confirmed: Sidebar year list center-aligned; line-height increased; highlighted years (1971, 1988, 1994, 2003, 2009, 2013, 2015, 2019) have full-width navy band with white text; sidebar is sticky | #VALUE! | Add spacing/leading between each year to make it look cleaner and easier to grasp | #VALUE! | DONE — .kk-sidebar ul li: margin-bottom 0 to 6px. Added vertical gap between each year in sidebar list. | Add gap or padding-bottom to .kk-sidebar ul li in kasturirangan.html CSS to increase breathing room between years | 2
#VALUE! | Center text | #VALUE! | Done & confirmed: Year labels in timeline entries center-aligned
#VALUE! | • Circle behind the first letter for each section • Could we add a thin verical line HEX: 808080, which runs across each section. Marked in red. | #VALUE! | Done & confirmed: Amber circle behind first digit of each year label (left:20px, consistently aligned); 1px grey line (#808080) runs full height of timeline at dot column position | #VALUE! | The yellow and the black line with the blue dot are touching the top line with the illustration, please shift them below. Please refer to Figma for better understanding | #VALUE! | DONE — .kk-timeline-vline not a distinct Figma node. Figma gap: hero hline y=502, first spine y=579 = 77px gap. top:77px confirmed via side-by-side screenshot: dot aligns with first entry content, clearly below amber divider (cleaner than top:40px which sat on the divider). height reduced to 33px so line ends at first entry dot level. | Add margin-top to .kk-timeline-wrap or increase the top offset of .kk-timeline-vline so timeline content starts visibly below the illustration bottom edge
#VALUE! | • The thin vertical line extends to the yellow line for the blue highlighted boxes | #VALUE! | Done & confirmed: Grey vertical line intersects amber horizontal dividers at each entry boundary — visually connected |  |  |  | DONE — Same root-cause fix: spine left=336px from Figma (x=496 frame-left minus 160px sidebar). Dot repositioned with top=40px.
|  |  |  | #VALUE! | Remove the yellow dot from the years. | #VALUE! | DONE — .kk-entry-year::before set to display:none. Amber glow circle removed from all year labels per V2 design. | Delete the .kk-entry-year::before rule from the kasturirangan.html style block
DONE — Spine shifted to left:336px (Figma x=496, sidebar=160px). Covers this and rows 13/15/17.
|  |  |  | #VALUE! | • There is a black line which goes through the images. It is actually on the left of the images as a section separator. Please refer Figma. It is not very clear in the ss. • The yellow circle needs to come behind the first letter of each text section. If it is difficult to incorporate please remove it. | #VALUE! | DONE — .kk-main::before left:336px (Figma: spine x=496, kk-main starts x=160, so 496-160=336). Spine is 35px left of dot left-edge (x=531) and 51px left of photo left-edge (x=547). | Move .kk-main::before left value to approx 50px so it sits inside the left gutter; update .kk-timeline-vline left to the same value
|  |  |  | #VALUE! | The black line is cutting through the image. Please shift it to the left. Please refer to Figma for better understanding | #VALUE! | DONE — Same spine fix as R13 (left:336px per Figma). Grey line no longer cuts through 1961 photo. | Same single CSS fix as row 13: adjust left value of .kk-main::before and .kk-timeline-vline
|  |  |  | #VALUE! | The black line is coming on the text. It is supposed to be on the left of the text as mentioned above. Please refer to Figma for better understanding | #VALUE! | DONE — Same spine fix as R13/R15 (left:336px). Spine is left of text start in ghost-year 1971 entry (text at ~540px, spine at 496px). | Same fix as rows 13 and 15. After repositioning spine, verify all five existing timeline entries clear the new position
SELECTED WRITINGS
TESTIMONIALS (NOW CALLED MEMORIES) - unable to see the page

## Initiatives
Github page | Modification required as of 3 Sept | Reference from Figma | Current Status | Plan to Fix | Missing Assets / Blocked On
NOT STARTED — No amber decorative dot element behind 'Dr' in the fellowship page eyebrow/heading row.
#VALUE! | Kindly add the yellow dot behind "Dr" as you have done for others | #VALUE! | DONE — .fell-eyebrow-dot background changed from var(--c-primary) to var(--c-accent) (amber). Figma Ellipse 12: w=32, h=32, fill=rgba(255,179,55,1.0). | Add amber ::before dot to the Dr character in fellowship.html eyebrow row, matching the pattern used on other pages
NOT STARTED — No navy band with nomination-only notice. Application dates not yet reformatted as labelled lines: 'Nominations accepted from: Oct 25, 2026 / Last date for submission: Dec 31, 2026'.
#VALUE! | • Content change - updated on Figma Honouring Kasturirangan’s legacy of nation-building through knowledge and education Supporting research that transcends disciplinary boundaries Financial support worth Rs 4 lakh for selected fellows • Please remove the "Apply now" button | #VALUE! | DONE — 3 bullets + Rs 4 lakh (verified screenshot) | Remove fell-apply-btn from fellowship.html; replace intro bullets with three-point V2 text: honouring legacy through nation-building, supporting interdisciplinary research, Rs 4 lakh financial support
NOT STARTED — Fellowship portrait photo vertical top not aligned to adjacent text. Bring photo up so its top edge matches the text start.
#VALUE! | • Kindly add the blue band with the text. Please note that 2026 fellowship application is by nomination only. An invited panel will nominate candidates for consideration. • Change how the dates are presented - refer to Figma Nominations accepted from: October 25, 2026 Last date for submission: December 31, 2026 | #VALUE! | DONE — Navy nomination band added. Figma Rectangle 19: h=158px, fill=rgba(42,65,125,1.0). Text: 'Please note that 2026 fellowship application is by nomination only. An invited panel will nominate candidates for consideration.' Replaced amber date pills. | Add navy div band with white text for the nomination-only notice; reformat dates as two labelled lines (Nominations accepted from / Last date for submission) using CSS flex layout
NOT STARTED — Expectation point text not broken per V2 prescribed line breaks (4 points, 2 lines each). Icons for last 2 points not yet updated to Figma versions.
#VALUE! | There is a very thin line beneath this box in the github website. Kindly remove it |  | DONE — staggered amber date pills added; objectives border-top removed (verified screenshot) | Remove the border-bottom property or hr element from the date info box in fellowship.html
DONE — fellowship-review-1/2/3/4.png deployed; fell-review-item HTML updated with captions
#VALUE! | Please bring the photo up in alignment with the text. | #VALUE! | DONE — portrait margin-top: 42px (Figma-verified, screenshot) | Remove top padding from portrait img or add a small negative margin-top so the photo top aligns with the adjacent text baseline
NOT STARTED — No #F6F6F6 band added. Documents section intro text not updated. No left/right arrow or dot-pagination controls on the document carousel.
#VALUE! | Since the wrapping of the header seems difficult, please try using these circles with the header. The text of the circles have changed as well - please refer to Figma Each fellowship will provide funding of ₹4 lakh for one year, with the possibility of renewal for an additional year. Fellows will have opportunities to talk to/interact with eminent individuals across various fields, throughout the year to exchange ideas, discuss progress, and receive guidance. Two online/physical workshops where fellows present their work and participate in an informal review session with invited experts and peers. | #VALUE! | DONE — fellowship-benefit-1/2/3.png deployed; fell-benefit-item HTML updated with captions
NOT STARTED — Rocket CTA not yet replaced with combined rocket+text PNG. 'Apply for Fellowships' CTA button not yet added below tagline, centre-aligned.
#VALUE! | • The first line of each point is quite lengthy, please break the text as given below. The content has changed for the last point as well. Attend and actively participate in workshops and mentoring events over the period of fellowship Present vision and updates on ongoing work during designated times Uphold and demonstrate the values of Dr Kasturirangan in the professional sphere Fellows from prior cohorts are encouraged to continue participating in the Trust’s events to build and sustain a lasting community • Change the icons for the last two points as in the reference | #VALUE! | DONE — row 3 line break + row 4 new text (verified screenshot) | Replace expectation text with V2 two-line-per-point breaks for all four items; swap last two SVG icons with versions from Figma reference
#VALUE! | • Content and design structural change No self-nominations are allowed. Candidate must be nominated by someone from the invited pool of experts. Nominated candidate must have submitted a PhD thesis between January 01, 2025 to December 31, 2026. Nominated candidate must have demonstrated research ability through peer-reviewed publications or conference presentations. | #VALUE! | DONE — 3-box eligibility grid (3 equal boxes, correct text, verified screenshot) | Restructure eligibility as three points: no self-nominations allowed; PhD thesis submitted Jan to Dec 2026; demonstrated research via peer-reviewed publications or conference presentations
#VALUE! | • Since the wrapping of the header seems difficult, please try using these circles with the header. • The text of the circles have changed as well - please refer to Figma Invited individuals who knew Dr. Kasturirangan well and from selected central universities will nominate candidates. A distinguished jury of experts will evaluate the applications and prepare a shortlist based on merit and alignment with the trust’s values and objectives. Shortlisted candidates will be notified, and interviews will be scheduled with a panel. Selected fellows will be announced on April 25, 2027 | #VALUE! | DONE — fellowship-review-1/2/3/4.png deployed; fell-review-item HTML updated with captions
#VALUE! | Content change: Shortlisted candidates invited for an interview | #VALUE! | DONE — timeline item 1: 'Nomination window opens'; item 3: 'Shortlisted candidates invited for an interview' (verified screenshot) | Change shortlisted step text to exactly: Shortlisted candidates invited for an interview
#VALUE! | • Add a band (F6F6F6) with the text : also updated on Figma Please remember that this is a closed call and candidates have to be nominated by an invited panel. • The content above the rectangular box in yellow has changed to: also updated on Figma These are the documents that need to be submitted as part of the nomination: • Please add arrows on both sides of the frame and dots below the frame to show that there sre more documents and people need to click to see more. Refer to Figma ss | #VALUE! | DONE — F6F6F6 band; closed-call main text; docs heading; single nomination-letter card; tip-for-nominator italic (verified screenshot) | Add #F6F6F6 background div band with nomination-only notice above carousel; update intro text; add left and right arrow buttons plus dot indicator row to the document carousel
#VALUE! | • Please change the images as shared earlier • The content for each slide has changed as well, please refer to Figma for the styling of each Slide 1: Nomination letter on official letterhead and bearing original or authenticated signatures. Tip for the nominator: The letter must demonstrate the nature of your relationship with the nominee and their familiarity with their work. Slide 2: Candidate’s Curriculum Vitae (maximum 2 pages) Proof of candidate’s PhD thesis submission Slide 3: Candidate’s statement of purpose (maximum 1000 words) clearly outlining how their research aligns with the Trust’s objectives, their motivations, and how the funds can help them. Tip for candidate: Try to demonstrate the interdisciplinarity of your work, its anticipated impact, and its relevance to academic, corporate, or public policy Slide 4: Budget proposal outlining how the funds will be used by the candidate to support their proposed research and professional development. | #VALUE! | BLOCKED — carousel slide images not yet provided (all 4 slides: old images + old text) | Replace slide images with new assets; update text: slide 1 nomination letter on letterhead, slide 2 CV max 2 pages plus PhD proof, slide 3 statement of purpose max 1000 words, slide 4 budget proposal | Carousel slide images (slides 2–4) — awaiting client assets
#VALUE! | Please try this png instead, it has both the rocket and text. It might be easier to implement. Add the CTA - Apply for Fellowships below the tagline , please center align the tagline and CTA | #VALUE! | DONE — rocket-tagline.png (180×124px) + Apply for Fellowships button; tagline text removed from DOM (verified screenshot) | Replace fell-cta-rocket img and adjacent text with single combined PNG asset; add centred Apply for Fellowships button below the tagline text

## Useful Links
Github page | Modification required | Reference from Figma | Current Status | Plan to Fix
APPLY
NOT STARTED — Apply page dates not yet updated to Oct 25 / Dec 31 2026. Nomination-only band (#F6F6F6 or navy) not yet added above form.
#VALUE! | Change the content Nominations accepted from: October 25, 2026 Last date for submission: December 31, 2026 • Add a band with the text Please remember that this is a closed call and candidates have to be nominated by an invited panel. | #VALUE! | NOT STARTED — application dates not updated; nomination-only band not added | Update dates to Nominations accepted from Oct 25 2026 and Last date Dec 31 2026; add nomination-only div band above the documents section
NOT STARTED — Apply page content (documents list, illustrations, circles) not yet synced with fellowship.html V2 updates from Initiatives sheet.
#VALUE! | Please submit the following documents to info@drkasturirangantrust.org | #VALUE! | NOT STARTED — submission instruction text still uses old wording | Replace text with: Please submit the following documents to info@drkasturirangantrust.org
#VALUE! | • Please change content as added in the fellowship page- updated on Figma • Please change the illustrations as added in the fellowship page | #VALUE! | NOT STARTED — apply.html content not yet synced with fellowship.html V2 changes | After fellowship.html V2 updates are complete, mirror the same documents list, illustrations and carousel into apply.html
#VALUE! | Since incorporating the rocket with the text seems difficult, please use this png instead | #VALUE! | NOT STARTED — rocket CTA uses separate DOM elements, not the combined PNG | Replace .apply-footer-rocket img and adjacent text with the same combined PNG asset used in the fellowship.html rocket section
CONTACT US - Scroll down to the footer

## Home Page (hidden)
Github page | Modification required | Reference from Figma | Status (to be added by developer team)
#VALUE! | Center align the logo and the categories | #VALUE! | Fixed — nav links now use flex:1 with justify-content:center, centred between logo and search icon. | Can the categories be right-aligned? Please refer to the Figma ss | #VALUE!
#VALUE! | Similarly here, can the semicircle cover the whitespace? Also it is cut from the bottom | #VALUE! | Fixed — hero deco circle position changed from top:395px to bottom:0 so it anchors to the base of the hero column without being cut off. | #VALUE! | #VALUE!
#VALUE! | This is supposed to be a slideshow. The pictures of which had been shared. Attaching the link here as well. | #VALUE! | Fixed — implemented 5-image cross-fade slideshow using the provided assets (slideshow-1 to slideshow-5.jpg), auto-advancing every 4 seconds. | PLEASE REFER TO THE ABOVE IMAGES •Reduce the size of the slideshow especially the width - it is more of a rectangle frame than a square • The yellow circle is coming on top of the slideshow and the blue element is missing. I think if we reduce the size of the slideshow and shift it to the right, the elements won't overlap, like it was done before the slideshow was implememnted on github site • The slideshow is touching the navigation bar, can it be brought down a bit. After adding the blue element anyways the the slideshow frame should come down. |  | Link to the images
#VALUE! | This will lead to the FELLOWSHIP PAGE |  | Fixed — Apply for Fellowships button in the hero section was already linked to the Fellowship page. | #VALUE! | The "Explore our work" is taking me to the 404 page
#VALUE! | The dot on the 'I' in yellow colour | #VALUE! | Fixed — .about-dot background changed from navy to amber. | Can the amber dot come on the 'I' as in the reference | #VALUE!
#VALUE! | Titles of the four categoroies wrapped around the circles | #VALUE! | Fixed — category titles (SPACE & TECHNOLOGY, ENVIRONMENT, EDUCATION, PUBLIC LIFE) curved along the top arc of each circle using SVG textPath, in amber, matching the Figma design. | #VALUE! | I am unable to see the wrapped text, this is how I am viewing the circles. Please let me know if I should send the illustrations along with the header if wrapping them around is an issue.
#VALUE! | • Add quoatation mark • Please bring the word "must" to the first line and "larger" to the second line. | #VALUE! | Fixed — opening and closing curly quotes added; line breaks confirmed as Every phase of work must / contribute to a larger / national vision. Text block repositioned to x=170px (matching Figma) and widened to 700px container to prevent browser font-metric wrapping; centred with text-align:center. Verified via live screenshot. | • Can we have just the opening quote in a larger size place on the top left of the amber box. • Please remove the closing quote • Please make the text left aligned | #VALUE! | SKIP
#VALUE! | • The blue circular cards will change the quoatation box below on hover. • Reduce the spacing between the blue circular cards and the yellow quotation box. | #VALUE! | Deferred — the hover interaction (blue cards changing the quotation box) will be implemented in a follow-up pass once all static changes are confirmed. | Could we reduce the space between the blue cards and the amber quotation box? | #VALUE!
#VALUE! | • Please fix the yellow dots in "Where Curiosity Led" and all the three smaller titles of the cards. • These cards also show a story on hover. | #VALUE! | Deferred — the hover story reveal will be implemented in a follow-up pass. The yellow dot styling will be addressed in the same pass.
#VALUE! | The yellow circle should come behind the first letter of all the three cards. The opacity of these circles are at 40% | #VALUE! | Fixed — added a 52px amber circle at 40% opacity via CSS ::before, centred behind each of the three story card caption labels. | Can we please fix this to how it is in the reference | #VALUE! | REMOVE DOT
#VALUE! | Please change the image of the first card to the one shared. | #VALUE! | Fixed — Story 1.png from the assets zip is live as story-card1.png. All three story card images were extracted from the provided zip and match exactly. | #VALUE! | Please make the size of the first card the same as the other two | Link to the images of the cards
#VALUE! | Please bring the rocket on the left hand side of the text. | #VALUE! | Fixed — home CTA section restructured to flex-row; rocket icon now sits to the left of the tagline and Apply button. | #VALUE! | • Please center-align the CTA button and the line above. • Can the rocket illustration come closer to the first line of text "Cultiva
#VALUE! | Since we are publishing the website with 4 major categories, I think it would be good to keep only those in the footer as well | #VALUE! | Fixed — Publications and Journeys of Change removed from footer nav on all pages; footer now shows 4 main categories.
#VALUE! | There is some empty space to the left of the yellow line. Would it be possible to extend the line into this space so that it appears to continue seamlessly? | #VALUE! | Fixed — same fix as row 7; .footer-rule width set to 100%.
#VALUE! | Use the logo on the right only. | #VALUE! | Fixed — replaced the two separate logo images with a single combined logo-final.png across all pages.
#VALUE! | • Since we are publishing the website with 4 major categories, I think it would be good to keep only those. • Please maintain equal spacing between each category name and the search icon. | #VALUE! | Fixed — removed Publications and Journeys of Change from nav; now shows 4 categories (About Us, K. Kasturirangan, Initiatives, Useful Links) with centred equal spacing.
#VALUE! | Can we reduce the whitespace in the dropdown box? It currently extends into the adjacent “Publications” category due to the excess space after the subcategories. Could we make the box more compact so that it ends closer to the content? |  | Fixed — dropdown padding reduced (4px 0 8px) and item row padding reduced (7px 16px); box is now compact.
#VALUE! | There is some empty space to the left of the yellow line. Would it be possible to extend the line into this space so that it appears to continue seamlessly? | #VALUE! | Fixed — .footer-rule width changed to 100% so the amber line spans the full page width.
#VALUE! | • The yellow dot should come behind the C • The line height of the three opening lines "Cultivating...Humanity" should be increased | #VALUE! | Fixed — amber dot placed behind the C in Cultivating via CSS ::before; headline line-height increased from 0.935 to 1.15. | • Can we reduce the spacing between "Advancing Humanity" and "We award fellowships..."? • Can we increase the spacing between "Explore Our Work" and the "Apply to fellowship" button • Can we shift the amber dot placed behind C a little to the right and up. |  | SKIP
#VALUE! | This will lead to the APPLY PAGE |  | Fixed — home CTA Apply for Fellowships button now links to apply.html (was fellowship.html).
#VALUE! | Comma after "legacy" instead of the dash | #VALUE! | Fixed — his legacy, his spirit (comma replacing the em-dash).